## Sheet1
Defects
Date Found | Description | Assigned | Hours Estimated | Hours Actual | Date Resolved
2013-10-07 | System crashed when duplicate email was provided for new user | Dan | 0.5 | 0.25 | 2013-10-07
2013-10-25 | System returning row number instead of emoployee number in ProjectInsert.PHP | Dan | 0.5 | 0.5 | 2013-10-25
2013-10-25 | Employee Asign to project bug | Dan | 0.5 | 0.5 | 2013-10-25
2013-11-09 | Update Sprint does not save selected Project | Dan | 0.5 | 0.5 | 2013-11-09
|  | Total | 1.5 | 1.75