## Sheet1
Iteration | Task | Subtask | Assigned | Duration | Remaining | Complete
1 | Inception | Vision | Team | 2 | 0 | Done
|  | Develop Plan | Dan | 2 | 0 | Done
|  | System Diagram | Team | 1 | 0 | Done
| Database Design for Iteration | UML Design |  | 1 | 1
|  | Implementation |  | 2 | 2
|  | Create Scriipts |  | 1 | 1
| Rough Interface | Design |  | 2 | 2
|  | Implementation |  | 2 | 2
| User Creation | UML Design |  | 1 | 1
|  | Implementation |  | 3 | 3
| Login | UML Design |  | 1 | 1
|  | Implementation |  | 2 | 2
| Role Creation | UML Design |  | 1 | 1
|  | Implementation |  | 3 | 3
| User Management | UML Design |  | 1 | 1
|  | Implementation |  | 2 | 2
| Role Management | UML Design |  | 1 | 1
|  | Implementation |  | 2 | 2
| Company Properties | UML Design |  | 1 | 1
|  | Implementation |  | 2 | 2
| Project Creation | UML Design |  | 1 | 1
|  | Implementation |  | 3 | 3 |  | Iteration 1
| Project Managemnet | UML Design |  | 1 | 1 |  | Planned | Completed
|  | Implementation |  | 1 | 1 |  | 39 | 5
2 | Epic Creation | UML Design |  | 1 | 1
|  | Implementation |  | 3 | 3
| Epic Management | UML Design |  | 1 | 1
|  | Implementation |  | 2 | 2
| Story Creation | UML Design |  | 1 | 1
|  | Implementation |  | 3 | 3
| Story Management | UML Design |  | 1 | 1
|  | Implementation |  | 2 | 2
| Work Recording | UML Design |  | 1 | 1
|  | Implementation |  | 3 | 3 |  | Iteration 2
| Work Management | UML Design |  | 1 | 1 |  | Planned | Completed
|  | Implementation |  | 2 | 2 |  | 21 | 0
3 | Gantt Chart | Design layout |  | 2 | 2 |  | Iteration 3
|  | Implement SQL |  | 15 | 15 |  | Planned | Completed
|  | Build Visualization |  | 15 | 15 |  | 32 | 0
| Total Work |  |  | 92 | 87
More reports for iteration 3 if time allows