## Slide 1: Team 3 Better Software
Gary Johns
Dan Lain
Jose Flores

## Slide 2: Overview
Project Plan
Increment 3
Bug Tracking
Prototype Demo
Code Walk Through
Joel Test
Survival Test
Final Presentation

## Slide 3: Project Plan
Due | Iteration | Task | Subtask | Assigned | Duration | Actual | Remaining | Complete |  |  | 
2-Oct | 1 | Inception | Vision | Team | 2 | 2 | 0 | Done |  |  | 
 |  |  | Develop Plan | Dan | 2 | 2 | 0 | Done |  |  | 
 |  |  | System Diagram | Team | 1 | 1 | 0 | Done |  |  | 
 |  | Database Design for Iteration | UML Design | Dan | 1 | 1 | 0 | Done |  |  | 
 |  |  | Implementation | Dan | 4 | 4 | 0 | Done |  |  | 
 |  |  | Create Scriipts | Dan | 1 | 1 | 0 | Done |  |  | 
 |  | Rough Interface | Design | Jose | 2 | 2 | 0 | Done |  |  | 
 |  |  | Implementation | Jose | 2 | 2 | 0 | Done |  |  | 
 |  | User Creation | UML Design | Gary | 1 | 1 | 0 | Done |  |  | 
 |  |  | Implementation | Gary | 3 | 3 | 0 | Done |  |  | 
 |  | Login | UML Design | Gary | 1 | 1 | 0 | Done |  |  | 
 |  |  | Implementation | Gary | 2 | 2 | 0 | Done |  |  | 
 |  | Role Creation | UML Design | Dan | 1 | 1 | 0 | Done |  |  | 
 |  |  | Implementation | Dan | 3 | 3 | 0 | Done |  |  | 
 |  | User Management | UML Design | Gary | 1 | 1 | 0 | Done |  |  | 
 |  |  | Implementation | Gary | 2 | 2 | 0 | Done |  |  | 
 |  | Role Management | UML Design | Dan | 1 | 1 | 0 | Done |  |  | 
 |  |  | Implementation | Dan | 2 | 2 | 0 | Done | Iteration 1 |  | 
 |  | Company Properties | UML Design | Jose | 1 | 1 | 0 | Done | Planned | Actual | Remaining
 |  |  | Implementation | Jose | 2 | 2 | 0 | Done | 35 | 35 | 0
28-Oct | 2 | Review Feedback |  | Team | 2 | 2 | 0 | Done |  |  | 
 |  | Implement Feedback |  | Team | 1 | 1 | 0 | Done |  |  | 
 |  | Project Creation | Implementation | Gary | 1 | 4 | 0 | Done |  |  | 
 |  | Project Managemnet | Implementation | Gary | 1 | 2 | 0 | Done |  |  | 
 |  | Epic Creation | Implementation | Dan | 3 | 3 | 0 | Done |  |  | 
 |  | Epic Management | Implementation | Dan | 2 | 1 | 0 | Done |  |  | 
 |  | Story Creation | Implementation | Dan | 3 | 4 | 0 | Done |  |  | 
 |  | Story Management | Implementation | Dan | 2 | 1 | 0 | Done |  |  | 
 |  | Sprint Creation | Implementation | Jose | 3 | 3 | 0 | Done |  |  | 
 |  | Sprint Management | Implementation | Jose | 2 | 2 | 0 | Done | Iteration 2 |  | 
 | 3 | Work Recording | Implementation | Jose | 3 | 3 | 0 | Done | Planned | Actual | Remaining
 | 3 | Work Management | Implementation | Jose | 2 | 2 | 0 | Done | 25 | 20 | 5
18-Nov | 3 | Review Feedback |  | Team | 2 | 2 | 0 | Done |  |  | 
 |  | Implement Feedback |  | Team | 2 | 2 | 0 | Done |  |  | 
 |  | Sprint Story Creation | Implementation | Dan | 4 | 4 | 0 | Done |  |  | 
 |  | Sprint Story Management | Implementation | Dan | 4 | 4 | 0 | Done |  |  | 
 |  | Reports | Design layout | Gary | 2 | 2 | 0 | Done | Iteration 3 |  | 
 |  |  | Implement SQL | Dan | 15 | 12 | 0 | Done | Planned | Actual | Remaining
 |  |  | Build Visualization | Dan | 15 | 12 | 0 | Done | 49 | 43 | 0
 |  | Total Work |  |  | 104 | 101 | 0 | Done |  |  | 

## Slide 4: Increment 3Deliverables
Review Feedback from Iteration 2
Implement Feedback from Iteration 2
Sprint Creation
Sprint Management
Reports Creation

## Slide 5: Joel Test
The Joel Test |  | Iteration 1 | Iteration 2 | Iteration 3
1 | Do you use source control? | 1 | 1 | 1
2 | Can you make a build in one step? | 1 | 1 | 1
3 | Do you make daily builds? | 1 | 1 | 1
4 | Do you have a bug database? | 0 | 1 | 1
5 | Do you fix bugs before writing new code? | 1 | 1 | 1
6 | Do you have an up-to-date schedule? | 1 | 1 | 1
7 | Do you have a spec? | 1 | 1 | 1
8 | Do programmers have quiet working conditions? | 1 | 1 | 1
9 | Do you use the best tools money can buy? | 0 | 0 | 
10 | Do you have testers? | 0 | 0 | 
11 | Do new candidates write code during their interview? | 0 | 0 | 
12 | Do you do hallway usability testing? | 0 | 1 | 1
 |  | 7 | 9 | 9

## Slide 6: Survival Test
Survival Test |  | Iteration 1 | Iteration 2 | Iteration 3
1 | Does the project have a clear, unambiguous vision statement or mission statement? | 2 | 2 | 2
2 | Do all team members believe the vision is realistic? | 2 | 2 | 2
3 | Does the project have a business case that details the business benefit and how the benefit will be measured? | 3 | 3 | 3
4 | Does the project have a user interface prototype that realistically and vividly demonstrates the functionality that the actual system will have? | 3 | 3 | 3
5 | Does the project have a detailed, written specification of what the software is supposed to do? | 2 | 2 | 2
6 | Did the project team interview people who will actually use the software (end users) early in the project and continue to involve them throughout the project? | 0 | 0 | 0
 | . |  |  | 
 | . |  |  | 
 | . |  |  | 
28 | Does the project team have all the technical expertise needed to complete the project? | 3 | 3 | 3
29 | Does the project team have expertise with the business environment in which the software will operate? | 2 | 2 | 2
30 | Does the project have a technical leader capable of leading the project successfully? | 3 | 3 | 3
31 | Are there enough people to do all the work required? | 2 | 2 | 2
32 | Does everyone work well together? | 2 | 1 | 1
33 | Is each person committed to the project? | 1 | 1 | 1
 | Totals | 103.5 | 115.5 | 117.5

## Slide 7: Bug Tracking
Defects |  |  |  |  | 
Date Found | Description | Assigned | Hours Estimated | Hours Actual | Date Resolved
10/7/2013 | System crashed when duplicate email was provided for new user | Dan | 0.50 | 0.25 | 10/7/2013
10/25/2013 | System returning row number instead of emoployee number in ProjectInsert.PHP | Dan | 0.5 | 0.5 | 10/25/2013
10/25/2013 | Employee Asign to project bug | Dan | 0.5 | 0.5 | 10/25/2013
11/9/2013 | Update Sprint does not save selected Project | Dan | 0.5 | 0.5 | 11/9/2013
 |  | Total | 1.50 | 1.75 | 

## Slide 8: Rough Interface - Demo

## Slide 9: Code Walk Through

## Slide 10: Final Presentation
?