## Sheet1
Iteration | Task | Subtask | Assigned | Duration | Remaining | Complete
1 | Inception | Vision | Team | 2 | 0 | Done
|  | Develop Plan | Dan | 2 | 0 | Done
|  | System Diagram | Team | 1 | 0 | Done
| Database Design for Iteration | UML Design | Dan | 1 | 0 | Done
|  | Implementation | Dan | 4 | 0 | Done
|  | Create Scriipts | Dan | 1 | 0 | Done
| Rough Interface | Design | Jose | 2 | 0 | Done
|  | Implementation | Jose | 2 | 0 | Done
| User Creation | UML Design | Gary | 1 | 0 | Done
|  | Implementation | Gary | 3 | 0 | Done
| Login | UML Design | Gary | 1 | 0 | Done
|  | Implementation | Gary | 2 | 0 | Done
| Role Creation | UML Design | Dan | 1 | 0 | Done
|  | Implementation | Dan | 3 | 0 | Done
| User Management | UML Design | Gary | 1 | 1
|  | Implementation | Gary | 2 | 2
| Role Management | UML Design | Dan | 1 | 0 | Done
|  | Implementation | Dan | 2 | 0 | Done | Iteration 1
| Company Properties | UML Design | Jose | 1 | 1 |  | Planned | Completed
|  | Implementation | Jose | 2 | 2 |  | 35 | 29
2 | Project Creation | UML Design |  | 1 | 1
|  | Implementation |  | 3 | 3
| Project Managemnet | UML Design |  | 1 | 1
|  | Implementation |  | 1 | 1
| Epic Creation | UML Design |  | 1 | 1
|  | Implementation |  | 3 | 3
| Epic Management | UML Design |  | 1 | 1
|  | Implementation |  | 2 | 2
| Story Creation | UML Design |  | 1 | 1
|  | Implementation |  | 3 | 3
| Story Management | UML Design |  | 1 | 1
|  | Implementation |  | 2 | 2
| Work Recording | UML Design |  | 1 | 1
|  | Implementation |  | 3 | 3 |  | Iteration 2
| Work Management | UML Design |  | 1 | 1 |  | Planned | Completed
|  | Implementation |  | 2 | 2 |  | 27 | 0
3 | Reports | Design layout |  | 2 | 2 |  | Iteration 3
|  | Implement SQL |  | 15 | 15 |  | Planned | Completed
|  | Build Visualization |  | 15 | 15 |  | 32 | 0
| Total Work |  |  | 94 | 65