## Task
Due | Iteration | Task | Subtask | Assigned | Duration | Actual | Remaining | Complete
2013-10-02 | 1 | Inception | Vision | Team | 2 | 2 | 0 | Done
|  |  | Develop Plan | Dan | 2 | 2 | 0 | Done
|  |  | System Diagram | Team | 1 | 1 | 0 | Done
|  | Database Design for Iteration | UML Design | Dan | 1 | 1 | 0 | Done
|  |  | Implementation | Dan | 4 | 4 | 0 | Done
|  |  | Create Scriipts | Dan | 1 | 1 | 0 | Done
|  | Rough Interface | Design | Jose | 2 | 2 | 0 | Done
|  |  | Implementation | Jose | 2 | 2 | 0 | Done
|  | User Creation | UML Design | Gary | 1 | 1 | 0 | Done
|  |  | Implementation | Gary | 3 | 3 | 0 | Done
|  | Login | UML Design | Gary | 1 | 1 | 0 | Done
|  |  | Implementation | Gary | 2 | 2 | 0 | Done
|  | Role Creation | UML Design | Dan | 1 | 1 | 0 | Done
|  |  | Implementation | Dan | 3 | 3 | 0 | Done
|  | User Management | UML Design | Gary | 1 | 1 | 0 | Done
|  |  | Implementation | Gary | 2 | 2 | 0 | Done
|  | Role Management | UML Design | Dan | 1 | 1 | 0 | Done
|  |  | Implementation | Dan | 2 | 2 | 0 | Done | Iteration 1
|  | Company Properties | UML Design | Jose | 1 | 1 | 0 | Done | Planned | Completed
|  |  | Implementation | Jose | 2 | 2 | 0 | Done | 35 | 35
2013-10-28 | 2 | Project Creation | UML Design | Gary | 1 |  | 1 | Done
|  |  | Implementation | Gary | 3 |  | 3 | Done
|  | Project Managemnet | UML Design | Gary | 1 |  | 1
|  |  | Implementation | Gary | 1 |  | 1
|  | Epic Creation | UML Design | Dan | 1 |  | 1
|  |  | Implementation | Dan | 3 |  | 3
|  | Epic Management | UML Design | Dan | 1 |  | 1
|  |  | Implementation | Dan | 1 |  | 2
|  | Story Creation | UML Design | Dan | 1 |  | 1
|  |  | Implementation | Dan | 3 |  | 3
|  | Story Management | UML Design | Dan | 1 |  | 1
|  |  | Implementation | Dan | 1 |  | 2
|  | Sprint Creation | UML Design | Jose | 1 |  | 1
|  |  | Implementation | Jose | 3 |  | 3
|  | Sprint Management | UML Design | Jose | 1 |  | 1
|  |  | Implementation | Jose | 2 |  | 2
|  | Work Recording | UML Design | Jose | 1 |  | 1
|  |  | Implementation | Jose | 3 |  | 3 |  | Iteration 2
|  | Work Management | UML Design | Jose | 1 |  | 1 |  | Planned | Completed
|  |  | Implementation | Jose | 2 |  | 2 |  | 32 | -2
2013-11-18 | 3 | Reports | Design layout |  | 2 |  | 2 |  | Iteration 3
|  |  | Implement SQL |  | 15 |  | 15 |  | Planned | Completed
|  |  | Build Visualization |  | 15 |  | 15 |  | 32 | 0
|  | Total Work |  |  | 99 |  | 66