## Sheet1
Defects
Date Found | Description | Assigned | Hours Estimated | Hours Actual | Date Resolved
2013-10-07 | System crashed when duplicate email was provided for new user | Dan | 0.5 | 0.25 | 2013-10-07
2013-10-25 | System returning row number instead of emoployee number in ProjectInsert.PHP | Dan | 0.5 | 0.5 | 2013-10-25
2013-10-25 | Employee Asign to project bug | Dan | 0.5 | 0.5 | 2013-10-25
2013-11-09 | Update Sprint does not save selected Project | Dan | 0.5 | 0.5 | 2013-11-09
2013-11-18 | Sprint initial story points not recording correctly | Dan | 0.5 | 0.25 | 2013-12-01
2013-11-26 | Name Not changing on all files. CompanyProperties business name should be on all headers not hard coded beter software | Dan | 0.5 | 0.25 | 2013-12-01
2013-11-26 | Remove Project list slider. Not used effectivly no longer makes sense. | Dan | 0.5 | 0.25 | 2013-12-01
|  | Total | 1.5 | 2.5