## Sheet1
The Joel Test |  | Iteration 1 | Iteration 2 | Iteration 3
1 | Do you use source control? | 1 | 1 | 1
2 | Can you make a build in one step? | 1 | 1 | 1
3 | Do you make daily builds? | 1 | 1 | 1
4 | Do you have a bug database? | 0 | 1 | 1
5 | Do you fix bugs before writing new code? | 1 | 1 | 1
6 | Do you have an up-to-date schedule? | 1 | 1 | 1
7 | Do you have a spec? | 1 | 1 | 1
8 | Do programmers have quiet working conditions? | 1 | 1 | 1
9 | Do you use the best tools money can buy? | 0 | 0
10 | Do you have testers? | 0 | 0
11 | Do new candidates write code during their interview? | 0 | 0
12 | Do you do hallway usability testing? | 0 | 1 | 1
|  | 7 | 9 | 9
Survival Test |  | Iteration 1 | Iteration 2 | Iteration 3
1 | Does the project have a clear, unambiguous vision statement or mission statement? | 2 | 2 | 2
2 | Do all team members believe the vision is realistic? | 2 | 2 | 2
3 | Does the project have a business case that details the business benefit and how the benefit will be measured? | 3 | 3 | 3
4 | Does the project have a user interface prototype that realistically and vividly demonstrates the functionality that the actual system will have? | 3 | 3 | 3
5 | Does the project have a detailed, written specification of what the software is supposed to do? | 2 | 2 | 2
6 | Did the project team interview people who will actually use the software (end users) early in the project and continue to involve them throughout the project? | 0 | 0 | 0
7 | Does the project have a detailed, written Software Development Plan? | 3 | 3 | 3
8 | Does the project’s task list include creation of an installation program, conversion of data from previous versions of the system, integration with third-party software, meetings with the customer, and other "minor" tasks? | 0 | 2 | 2
9 | Were the schedule and budget estimates officially updated at the end of the most recently completed phase? | 3 | 3 | 3
10 | Does the project have detailed, written architecture and design documents? | 2 | 2 | 2
11 | Does the project have a detailed, written Quality Assurance Plan that requires design and code reviews in addition to system testing? | 1 | 1 | 1
12 | Does the project have a detailed Staged Delivery Plan for the software, which describes the stages in which the software will be implemented and delivered? | 3 | 3 | 3
13 | Does the project’s plan include time for holidays, vacation days, sick days, and ongoing training, and are resources allocated at less than 100 percent? | 3 | 3 | 3
14 | Was the project plan, including the schedule, approved by the development team, the quality assurance team, and the technical writing team—in other words, the people responsible for doing the work? | 3 | 3 | 3
15 | Has a single key executive who has decision-making authority been made responsible for the project, and does the project have that person’s active support? | 1 | 1 | 1
16 | Does the project manager’s workload allow him or her to devote an adequate amount of time to the project? | 3 | 3 | 3
17 | Does the project have well-defined, detailed milestones ("binary milestones") that are considered to be either 100 percent done or 100 percent not done? | 3 | 3 | 3
18 | Can a project stakeholder easily find out which of these binary milestones have been completed? | 3 | 3 | 3
19 | Does the project have a feedback channel by which project members can anonymously report problems to their own managers and upper managers? | 0 | 3 | 3
20 | Does the project have a written plan for controlling changes to the software’s specification? | 0 | 0 | 0
21 | Does the project have a Change Control Board that has final authority to accept or reject proposed changes? | 2 | 2 | 2
22 | Are planning materials and status information for the project—including effort and schedule estimates, task assignments, and progress compared to the plan thus far—available to every team member? | 3 | 3 | 3
23 | Is all source code placed under automated revision control? | 3 | 3 | 3
24 | Does the project environment include the basic tools needed to complete the project, including defect tracking software, source code control, and project management software? | 2 | 3 | 3
25 | Does the project plan articulate a list of current risks to the project? Has the list been updated recently? | 0 | 3 | 3
26 | Does the project have a project risk officer who is responsible for identifying emerging risks to the project? | 3 | 3 | 3
27 | If the project uses subcontractors, does it have a plan for managing each subcontract organization and a single person in charge of each one? (Give the project full score if it doesn’t use subcontractors.) | 3 | 3 | 3
28 | Does the project team have all the technical expertise needed to complete the project? | 3 | 3 | 3
29 | Does the project team have expertise with the business environment in which the software will operate? | 2 | 2 | 2
30 | Does the project have a technical leader capable of leading the project successfully? | 3 | 3 | 3
31 | Are there enough people to do all the work required? | 2 | 2 | 2
32 | Does everyone work well together? | 2 | 1 | 1
33 | Is each person committed to the project? | 1 | 1 | 1
| Totals | 103.5 | 115.5 | 117.5

## Sheet2
Survival Test |  | Iteration 1 | Iteration 2 | Iteration 3
1 | Does the project have a clear, unambiguous vision statement or mission statement? | 2 | 2 | 2
2 | Do all team members believe the vision is realistic? | 2 | 2 | 2
3 | Does the project have a business case that details the business benefit and how the benefit will be measured? | 3 | 3 | 3
4 | Does the project have a user interface prototype that realistically and vividly demonstrates the functionality that the actual system will have? | 3 | 3 | 3
5 | Does the project have a detailed, written specification of what the software is supposed to do? | 2 | 2 | 2
6 | Did the project team interview people who will actually use the software (end users) early in the project and continue to involve them throughout the project? | 0 | 0 | 0
.
.
.
28 | Does the project team have all the technical expertise needed to complete the project? | 3 | 3 | 3
29 | Does the project team have expertise with the business environment in which the software will operate? | 2 | 2 | 2
30 | Does the project have a technical leader capable of leading the project successfully? | 3 | 3 | 3
31 | Are there enough people to do all the work required? | 2 | 2 | 2
32 | Does everyone work well together? | 2 | 1 | 1
33 | Is each person committed to the project? | 1 | 1 | 1
| Totals | 103.5 | 115.5 | 117.5